## 2019 Programming
UPDTYEAR | SITE_REF | ADDRESS1 | ADDRESS2 | EASTING | NORTHING | HMSA | LASUB | SITE_SIZE | OWNER1 | OWNER2 | TENURE | PRIVTEN | SRTEN | INTTEN | TENNOTE | BUILDER | PLANSTAT | SPGR | DEVTYPE | CONSENT | APP | FST_IN_ELS | CON_IN_ELS | FST_IN_EFF | CON_IN_EFF | CAPACITY | TOTAL_BUILT | REMAINDER | COMPLETIONS PRE 2012 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | TOTAL 7 YEAR PROGRAMMING | POST_7YEAR | DISPUTED | SITE_CONSTRAINTS
2019 | ED0002 | LENNOX CASTLE (Conversion) | LENNOXTOWN | 260592 | 678301 | SGNE | ST | 0.2 | PRIV | ALLIED IRISH BANK | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | CONV-NU |  |  | 1997 | 1997 | 1997 | 0 | 31 | 0 | 31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31 | 0 | PHY
2019 | ED0071A | BISHOPBRIGGS TOWN CENTRE (HIGH & SURROUNDS) | BISHOPBRIGGS | 261232 | 670347 | SGNE | ST | 0.9 | PRIV | BARRATT WEST SCOTLAND | PRIV | OO |  |  |  | BARRATT WEST SCOTLAND | ALPS |  | NB-BU |  |  | 2007 | 2007 | 2007 | 0 | 40 | 0 | 40 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | OWN
2019 | ED0071B | BISHOPBRIGGS TOWN CENTRE (HIGH & SURROUNDS) | BISHOPBRIGGS | 261232 | 670347 | SGNE | ST | 0.1 | PRIV | WM MORRISON SUPERMARKETS Plc | SR |  | RSL |  |  | UNKNOWN | ALPS |  | NB-BU |  |  | 2007 | 2007 | 2007 | 0 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | OWN
2019 | ED0083A | MACDONALD CRESCENT | TWECHAR | 270019 | 675042 | SGNE | ST | 2.73 | PRIV | UNKNOWN | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-GNU |  |  | 2010 | 2010 | 0 | 0 | 69 | 0 | 69 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69 | 0 | MARK
2019 | ED0088 | GLEN SHIRVA ROAD (MAIN) | TWECHAR | 269822 | 675693 | SGNE | ST | 1.03 | LA | EDC | SR |  | RSL |  |  | PLACES FOR PEOPLE | ALPS |  | NB-GU |  |  | 2010 | 2010 | 0 | 0 | 29 | 0 | 29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | OTH
2019 | ED0041D | LENNOX CASTLE HOSPITAL PHASE 3 | LENNOXTOWN | 260606 | 678302 | SGNE | ST | 3.01 | OTH | NHS | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BNU |  |  | 2003 | 2003 | 2003 | 0 | 60 | 0 | 60 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | PHY
2019 | ED0041E | LENNOX CASTLE HOSPITAL PHASE 4 | LENNOXTOWN | 260606 | 678302 | SGNE | ST | 3.8 | OTH | NHS | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BNU |  |  | 2003 | 2003 | 2003 | 0 | 78 | 0 | 78 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | PHY
2019 | ED0083B | MACDONALD CRESCENT | TWECHAR | 270019 | 675042 | SGNE | ST | 1 | PRIV | UNKNOWN | SR |  | RSL |  |  | UNKNOWN | ALPS |  | NB-GU |  |  | 2010 | 2010 | 0 | 0 | 23 | 0 | 23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | MARK
2019 | ED0176A | ACRE VALLEY NURSERY | TORRANCE | 261913 | 674613 | SGNE | ST | 0.8 | PRIV | UNKNOWN | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BU |  |  | 2017 | 2017 | 2017 | 0 | 7 | 0 | 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | OWN
2019 | ED0176B | ACRE VALLEY NURSERY | TORRANCE | 261913 | 674613 | SGNE | ST | 0.1 | PRIV | UNKNOWN | SR |  | RSL |  |  | UNKNOWN | ALPS |  | NB-BU |  |  | 2017 | 2017 | 2017 | 0 | 3 | 0 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | OWN
2019 | EDBM0073F | KILMARDINNY SOUTH SITE | BEARSDEN | 255437 | 672580 | GGNW | BM | 0.9 | PRIV | UNKNOWN | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BU |  |  | 1993 | 1993 | 1993 | 0 | 30 | 0 | 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | OWN
2019 | ED0138 | FORMER CHURCH, 2B CRARAE AVENUE | BEARSDEN | 254191 | 670517 | GGNW | BM | 0.18 | PRIV | ESK PROPERTY LLP | PRIV | OO |  |  |  | ESK PROPERTY LLP | CONS |  | NB-BU | DETL | TP/ED/16/0311 | 2013 | 2013 | 2013 | 0 | 10 | 0 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | LEGAL
2019 | ED0183 | SADDLERS BRAE FARM | KIRKINTILLOCH | 268355 | 674346 | SGNE | ST | 0.24 | PRIV | UNKNOWN | PRIV | OO |  |  |  | UNKNOWN | CONS |  | NB-GNU | OUTL | TP/ED/16/0367 | 2017 | 2017 | 2017 | 0 | 4 | 0 | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | MARK
2019 | ED0105 | WESTER GADLOCH FARM | LENZIE | 264411 | 671360 | SGNE | ST | 0.62 | PRIV | CALEDONIAN PROPERTIES LTD | PRIV | OO |  |  |  | CALEDONIAN PROPERTIES LTD | PROP |  | CONV-NU | LAPD | TP/ED/14/0833 | 2012 | 2012 | 2012 | 0 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | OWN
2019 | ED0145B | STRATHBLANE ROAD (No18) | MILNGAVIE | 255765 | 674556 | GGNW | BM | 0.01 | LA | EDC | SR |  | LA |  |  | EDC | ALPS |  | NB-BU |  |  | 2015 | 2015 | 2015 | 2015 | 1 | 0 | 1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | MARK
2019 | ED0163 | LOCHMILL FARM- ANTERMONY ROAD | MILTON OF CAMPSIE | 266716 | 676438 | SGNE | ST | 0.73 | PRIV | HCS CONSTRUCTION | PRIV | OO |  |  |  | HCS CONSTRUCTION | COMM |  | CONV-NU | DETL | TP/ED/13/0382 | 2016 | 2016 | 2016 | 2016 | 8 | 6 | 2 |  |  |  | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | UNCON
2019 | ED0177A | WEST CARLSTON GARDEN CENTRE (CAMPSIE ROAD) | TORRANCE | 262506 | 674576 | SGNE | ST | 1.01 | PRIV | DAWN HOMES LTD | PRIV | OO |  |  |  | DAWN HOMES LTD | COMM |  | NB-BNU | DETL | TP/ED/16/0325 | 2017 | 2017 | 2017 | 2017 | 16 | 14 | 2 |  |  |  | 0 | 0 | 0 | 0 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | UNCON
2019 | ED0167B | BALMORE GARDEN NURSERY | BALMORE | 260489 | 673442 | SGNE | ST | 0.1 | PRIV | CALEDONIAN PROPERTIES | SR |  | LA |  |  | EDC | ALPS |  | NB-BNU |  |  | 2017 | 2017 | 2017 | 2017 | 3 | 0 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | LU
2019 | ED0172B | DUNTIBLAE | KIRKINTILLOCH | 267374 | 673094 | SGNE | ST | 0.1 | PRIV | TAYLOR WIMPEY WEST SCOTLAND Ltd | SR |  | LA |  |  | EDC | ALPS |  | NB-GU |  |  | 2017 | 2017 | 2017 | 2017 | 3 | 0 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | MARK
2019 | ED0191C | FORMER ST AGATHA'S PRIMARY (AFFORDABLE) | KIRKINTILLOCH | 267929 | 673622 | SGNE | ST | 0.1 | LA | EDC | SR |  | LA |  |  | EDC | CONS |  | NB-BNU | DETL | TP/ED/17/0831 | 2019 | 2019 | 2019 | 2019 | 3 | 0 | 3 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | PHY
2019 | ED0144A | INVERORAN DRIVE (KESSINGTON) | BEARSDEN | 256092 | 671451 | GGNW | BM | 2.5 | PRIV | MANSELL HOMES | PRIV | OO |  |  |  | MANSELL HOMES | COMM |  | NB-GU | DETL | TP/ED/14/0602 | 2015 | 2015 | 2015 | 2015 | 59 | 56 | 3 |  |  |  | 0 | 0 | 7 | 27 | 22 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | UNCON
2019 | ED0155 | REGENT STREET (LAIRDSLAND CANTEEN) | KIRKINTILLOCH | 265151 | 673812 | SGNE | ST | 0.1 | LA | EDC | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BU |  |  | 2015 | 2015 | 2015 | 2015 | 4 | 0 | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | MARK
2019 | ED0177B | WEST CARLSTON GARDEN CENTRE (CAMPSIE ROAD) | TORRANCE | 262506 | 674576 | SGNE | ST | 1 | PRIV | DAWN HOMES LTD | PRIV | OTH |  | SE |  | EDC | CONS |  | NB-BNU | DETL | TP/ED/16/0325 | 2017 | 2017 | 2017 | 2017 | 4 | 0 | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | UNCON
2019 | ED0181 | DRYMEN ROAD (No172) | BEARSDEN | 254036 | 672531 | GGNW | BM | 0.14 | PRIV | BALMORE CONSTRUCTION | PRIV | OO |  |  |  | BALMORE CONSTRUCTION | COMM |  | NB-BU | DETL | TP/ED/14/0906 | 2017 | 2017 | 2017 | 2017 | 4 | 0 | 4 |  |  |  | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | UNCON
2019 | ED0089 | 1 GLEN SHIRVA ROAD | TWECHAR | 269955 | 675873 | SGNE | ST | 0.04 | RSL | CASTLEROCK EDINVAR HOUSING ASSOCIATION | SR |  | RSL |  |  | CASTLEROCK EDINVAR HOUSING ASSOCIATION | ALPS |  | NB-BU |  |  | 2010 | 2010 | 2011 | 2019 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | OTH
2019 | ED0145A | STRATHBLANE ROAD (No18) | MILNGAVIE | 255765 | 674554 | GGNW | BM | 0.1 | LA | EDC | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BU |  |  | 2015 | 2015 | 2015 | 2015 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 5 | 0 | 0 | MARK
2019 | ED0158B | CAMPSIE GOLF CLUB (CROW ROAD) | LENNOXTOWN | 262696 | 678672 | SGNE | ST | 0.2 | PRIV | CAMPSIE GOLF CLUB | PRIV | OTH |  | SE |  | EDC | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | INFRA
2019 | ED0168B | BIRNAM CRESCENT | BEARSDEN | 256043 | 672264 | GGNW | BM | 0.1 | PRIV | CALA HOMES WEST SCOTLAND LTD | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | CONS |  | NB-GU | DETL | TP/ED/17/0511 | 2017 | 2017 | 2017 | 2017 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | UNCON
2019 | ED0187 | MAIN STREET SOUTH | TORRANCE | 262007 | 673970 | SGNE | ST | 0.29 | LA | EDC | SR |  | LA |  |  | TRUST HOUSING ASSOCIATION | PROP |  | NB-BU |  |  | 2017 | 2017 | 2017 | 2017 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | PHY
2019 | ED0178 | SWITCHBACK RD (No8) | BEARSDEN | 254730 | 670909 | GGNW | BM | 0.37 | PRIV | MCCARTHY & STONE RETIREMENT LIFESTYLES Ltd | PRIV | OO |  |  |  | MCCARTHY & STONE RETIREMENT LIFESTYLES Ltd | COMM |  | NB-BU | DETL | TP/ED/16/0293 | 2017 | 2017 | 2017 | 2017 | 23 | 18 | 5 |  |  |  | 0 | 0 | 0 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | UNCON
2019 | ED0190 | WATSHOD FARM, CAMPSIE ROAD | MILTON OF CAMPSIE | 264807 | 675484 | SGNE | ST | 1.5 | PRIV | RALSTON CONTRACTS LTD | PRIV | OO |  |  |  | RALSTON CONTRACTS LTD | COMM |  | NB-GNU | DETL | TP/ED/17/0199 | 2019 | 2019 | 2019 | 2019 | 5 | 0 | 5 |  |  |  | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | UNCON
2019 | ED0150 | BLACKTHORN GROVE | LENZIE | 264690 | 672236 | SGNE | ST | 0.2 | LA | EDC | SR |  | LA |  |  | EDC | CONS |  | NB-BU | DETL | TP/ED/18/0367 | 2015 | 2015 | 2015 | 2015 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | UNCON
2019 | ED0159 | EAST OF ALDESSAN HOUSE | CLACHAN OF CAMPSIE | 261110 | 679580 | SGNE | ST | 0.84 | PRIV | LAND AND PROPERTY HOLDINGS Ltd | PRIV | OO |  |  |  | ROSSIE STEADINGS Ltd | CONS |  | NB-GU | DETL | TP/ED/17/0662 | 2015 | 2015 | 2015 | 2015 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | LEGAL
2019 | ED0191A | FORMER ST AGATHA'S PRIMARY SCHOOL (CONVERSION) | KIRKINTILLOCH | 267936 | 673668 | SGNE | ST | 0.21 | LA | EDC | PRIV | OO |  |  |  | PANACEA PROPERTY | CONS |  | CONV-NU | DETL | TP/ED/17/0831 | 2019 | 2019 | 2019 | 2019 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | PHY
2019 | ED0191B | FORMER ST AGATHA'S PRIMARY SCHOOL (NEW BUILD) | KIRKINTILLOCH | 267956 | 673625 | SGNE | ST | 0.1 | LA | EDC | PRIV | OO |  |  |  | PANACEA PROPERTIES | CONS |  | NB-BNU | DETL | TP/ED/17/0831 | 2019 | 2019 | 2019 | 2019 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | PHY
2019 | ED0160 | BALDORAN HOUSE- CAMPSIE ROAD | MILTON OF CAMPSIE | 264851 | 676865 | SGNE | ST | 1.1 | PRIV | ALEXANDER HART PROPERTIES | PRIV | OO |  |  |  | ALEXANDER HART PROPERTIES | COMM |  | NB-GNU | DETL | TP/ED/14/0080 | 2015 | 2015 | 2015 | 2015 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | UNCON
2019 | ED0185 | DAVID GRAY DRIVE/ FOSSIL GROVE | KIRKINTILLOCH | 267173 | 674190 | SGNE | ST | 0.12 | LA | EDC | SR |  | LA |  |  | EDC | CONS |  | NB-BU | DETL | TP/ED/17/0296 | 2017 | 2017 | 2017 | 2017 | 6 | 0 | 6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | UNCON
2019 | ED0167A | BALMORE GARDEN NURSERY | BALMORE | 260489 | 673442 | SGNE | ST | 0.5 | PRIV | CALEDONIAN PROPERTIES | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-BNU |  |  | 2017 | 2017 | 2017 | 2017 | 7 | 0 | 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | LU
2019 | ED0169 | CASTLEHILL FARM | BEARSDEN | 252613 | 672574 | GGNW | BM | 0.2 | PRIV | BUCHANAN FAMILY | PRIV | OO |  |  |  | FAIRBRIGHT HOMES Ltd | ALPS |  | NB-GU |  | TP/ED/18/0569 | 2017 | 2017 | 2017 | 2017 | 7 | 0 | 7 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 7 | 0 | 0 | INFRA
2019 | ED0147 | KELVINDALE NURSERY | TORRANCE | 262028 | 674241 | SGNE | ST | 0.2 | LA | EDC | SR |  | LA |  |  | EDC | ALPS |  | NB-BU |  |  | 2015 | 2015 | 2015 | 2015 | 8 | 0 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | LU
2019 | ED0170B | CROFTHEAD (NORTH BISHOPBRIGGS) | BISHOPBRIGGS | 262050 | 672339 | SGNE | ST | 0.1 | PRIV | CALEDONIAN PROPERTIES LTD | SR |  | LA |  |  | EDC | ALPS |  | NB-BNU |  |  | 2017 | 2017 | 2017 | 2017 | 8 | 0 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | UNCON
2019 | ED0161C | BRAE'S OF YETTS | KIRKINTILLOCH | 268034 | 673733 | SGNE | ST | 0.5 | PRIV | BARRATT WEST SCOTLAND | PRIV | OTH |  | SE |  | HILLHEAD HOUSING ASSOCIATION | CONS |  | NB-GU | DETL | TP/ED/16/0600 | 2015 | 2015 | 2015 | 2015 | 8 | 0 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | UNCON
2019 | ED0165 | BANKELL FARM | MILNGAVIE | 257180 | 675490 | SGNE | ST | 0.3 | PRIV | BANKELL DEVELOPMENTS LTD | PRIV | OO |  |  |  | BANKELL DEVELOPMENTS LTD | COMM |  | CONV-NU | DETL | TP/ED/16/0205 | 2016 | 2016 | 2016 | 2016 | 8 | 0 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | UNCON
2019 | ED0164 | 10 OXGANG HOLDINGS | KIRKINTILLOCH | 266620 | 673497 | SGNE | ST | 0.13 | PRIV | CREDITORS | PRIV | OO |  |  |  | WILLIAM HOLLAND HOMES (IN ADMINISTRATION) | COMM |  | NB-BU | DETL | TP/ED/14/0706 | 2016 | 2016 | 2016 | 2016 | 8 | 0 | 8 |  |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | OTH
2019 | ED0171B | CHRYSTON ROAD SOUTH (FAULDHEAD) | KIRKINTILLOCH | 267777 | 672745 | SGNE | ST | 0.1 | PRIV | CALA HOMES WEST SCOTLAND Ltd | SR |  | LA |  |  | EDC | ALPS |  | NB-GU |  |  | 2017 | 2017 | 2017 | 2017 | 9 | 0 | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 9 | 0 | 0 | MARK
2019 | ED0078E | ROB ROY FC / ADAMSLIE - PHASE 2 | KIRKINTILLOCH | 264455 | 673715 | SGNE | ST | 0.2 | PRIV | DAWN HOMES Ltd | PRIV | OTH |  | SE |  | EDC | CONS |  | NB-BU | DETL | TP/ED/17/0052 | 2008 | 2008 | 2008 | 2008 | 9 | 0 | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | INFRA
2019 | EDBM0073D | KILMARDINNY - AFFORDABLE SITE 2 | BEARSDEN | 255584 | 673251 | GGNW | BM | 0.1 | LA | EDC | PRIV | OTH |  | SE |  | EDC | CONS |  | NB-BU | DETL | TP/ED/15/0944 | 1993 | 1993 | 1993 | 2011 | 9 | 0 | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | UNCON
2019 | ED0166 | NETHERTON FARM LANE- OFF SWITCHBACK ROAD | BEARSDEN | 254577 | 669952 | GGNW | BM | 0.3 | PRIV | S & A KILCOYNE | PRIV | OO |  |  |  | SJD Construction | CONS |  | NB-BU | DETL | TP/ED/15/0382 | 2016 | 2016 | 2016 | 2016 | 9 | 0 | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | MARK
2019 | ED0085 | CAMPSIE VIEW / FORMER RECREATION CENTRE | LENNOXTOWN | 263056 | 677566 | SGNE | ST | 0.31 | LA | EDC | SR |  | LA |  |  | EDC | COMM |  | NB-GU | DETL | TP/ED/17/0397 | 2010 | 2010 | 2012 | 2015 | 9 | 0 | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | UNCON
2019 | ED0086 | KEYSTONE ROAD | MILNGAVIE | 255634 | 673976 | GGNW | BM | 0.25 | LA | EDC | SR |  | LA |  |  | EDC | COMM |  | NB-BU | DETL | TP/ED/17/0294 | 2010 | 2010 | 2013 | 2013 | 9 | 0 | 9 |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | UNCON
2019 | EDSK0137 | THOMAS MUIR AVE | BISHOPBRIGGS | 261256 | 669713 | SGNE | ST | 0.5 | PRIV | VARWELL LTD | PRIV | OO |  |  |  | VARWELL LTD | ALPS |  | NB-GU |  |  | 1981 | 1981 | 2017 | 2017 | 10 | 0 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | OWN
2019 | ED0102B | MEADOWBURN AVENUE | LENZIE | 266569 | 671984 | SGNE | ST | 0.1 | PRIV | UNKNOWN | SR |  | LA |  |  | EDC | ALPS |  | NB-GNU |  |  | 2012 | 2012 | 2012 | 2012 | 10 | 0 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | PHY
2019 | ED0140B | THORN ROAD (GOLF COURSE) | BEARSDEN | 253235 | 672195 | GGNW | BM | 1 | PRIV | BEARSDEN GOLF CLUB | SR |  | RSL |  |  | UNKNOWN | ALPS |  | NB-GU |  | TP/ED/19/0067 | 2015 | 2015 | 2015 | 2015 | 10 | 0 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 0 | INFRA
2019 | ED0172A | DUNTIBLAE | KIRKINTILLOCH | 267374 | 673094 | SGNE | ST | 0.4 | PRIV | TAYLOR WIMPEY WEST SCOTLAND Ltd | PRIV | OO |  |  |  | TAYLOR WIMPEY WEST SCOTLAND Ltd | ALPS |  | NB-GU |  |  | 2017 | 2017 | 2017 | 2017 | 10 | 0 | 10 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0 | 0 | MARK
2019 | ED0186 | TOWNHEAD (No's 85 to 97) | KIRKINTILLOCH | 265647 | 673595 | SGNE | ST | 0.16 | RSL | TRUST HOUSING ASSOCIATION | SR |  | RSL |  |  | TRUST HOUSING ASSOCIATION | CONS |  | NB-BU | DETL | TP/ED/18/0033 | 2017 | 2017 | 2017 | 2017 | 11 | 0 | 11 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | UNCON
2019 | ED0038C | BROOMHILL HOSPITAL SITE | KIRKINTILLOCH | 266147 | 674606 | SGNE | ST | 0.1 | PRIV | CALA HOMES WEST SCOTLAND Ltd | SR |  | MMRS |  |  | LINK HOUSING ASSOCIATION | ALPS |  | NB-GU | PEND | TP/ED/17/0857 | 2003 | 2003 | 2003 | 2014 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | UNCON
2019 | ED0055B | CRAIGDHU RD, FIRE STATION FIELD | MILNGAVIE | 254497 | 674201 | GGNW | BM | 0.1 | PRIV | MCCARTHY AND STONE | SR |  | RSL |  |  | SANCTUARY | CONS |  | NB-GU | DETL | TP/ED/16/0823 | 2005 | 2017 | 2005 | 2017 | 12 | 0 | 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | UNCON
2019 | ED0099C | CADDER WORKS/ JELLYHILL | BISHOPBRIGGS | 260947 | 671671 | SGNE | ST | 0.1 | PRIV | CALA HOMES WEST SCOTLAND LTD | SR |  | MMRS |  |  | LINK HOUSING ASSOCIATION | CONS |  | NB-BU | DETL | TP/ED/17/0051 | 2012 | 2012 | 2015 | 2015 | 12 | 0 | 12 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | UNCON
2019 | EDBM0073B | KILMARDINNY - CALA PHASE 1 | BEARSDEN | 255584 | 673251 | GGNW | BM | 3.72 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | COMM |  | NB-BU | DETL | TP/ED/13/0686 | 1993 | 1993 | 1993 | 2011 | 135 | 123 | 12 |  |  |  | 0 | 0 | 2 | 61 | 60 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | UNCON
2019 | ED0173B | LENNOXLEA | LENNOXTOWN | 263473 | 677085 | SGNE | ST | 0.1 | PRIV | TAYLOR WIMPEY WEST SCOTLAND Ltd | SR |  | RSL |  |  | UNKNOWN | ALPS |  | NB-GU |  |  | 2017 | 2017 | 2017 | 2017 | 13 | 0 | 13 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 13 | 0 | 0 | MARK
2019 | ED0175B | BIRDSTON ROAD | MILTON OF CAMPSIE | 265261 | 675888 | SGNE | ST | 0.1 | PRIV | CALA HOMES WEST SCOTLAND Ltd | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | CONS |  | NB-GU | DETL | TP/ED/17/0486 | 2017 | 2017 | 2017 | 2017 | 14 | 0 | 14 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | UNCON
2019 | ED0168A | BIRNAM CRESCENT | BEARSDEN | 256043 | 672264 | GGNW | BM | 2.3 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | COMM |  | NB-GU | DETL | TP/ED/17/0511 | 2017 | 2017 | 2017 | 2017 | 15 | 1 | 14 |  |  |  | 0 | 0 | 0 | 0 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | UNCON
2019 | ED0158A | CAMPSIE GOLF CLUB (CROW ROAD) | LENNOXTOWN | 262696 | 678672 | SGNE | ST | 1 | PRIV | CAMPSIE GOLF CLUB | PRIV | OO |  |  |  | UNKNOWN | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 15 | 0 | 15 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 8 | 15 | 0 | 0 | INFRA
2019 | ED0188B | ST MUNGO STREET | BISHOPBRIGGS | 260902 | 669985 | SGNE | ST | 0.15 | RSL | TRUST HOUSING ASSOCIATION | SR |  | MMRS |  |  | TRUST HOUSING ASSOCIATION | CONS |  | NB-BU | DETL | TP/ED/17/0717 | 2018 | 2018 | 2018 | 2018 | 16 | 0 | 16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | UNCON
2019 | ED0182B | HIGH STREET VAN HIRE (NO'S 62 - 72) PHASE 2 | KIRKINTILLOCH | 265413 | 674144 | SGNE | ST | 0.2 | PRIV | UNKNOWN | SR |  | RSL |  |  | CLYDE VALLEY HOUSING ASSOCIATION | PROP |  | NB-BU | PEND | TP/ED/17/0930 | 2018 | 2018 | 2018 | 2018 | 16 | 0 | 16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | LEGAL
2019 | ED0182C | HIGH STREET VAN HIRE (NO'S 62 - 72) PHASE 3 | KIRKINTILLOCH | 265438 | 674134 | SGNE | ST | 0.5 | PRIV | UNKNOWN | SR |  | RSL |  |  | CLYDE VALLEY HOUSING ASSOCIATION | PROP |  | NB-BU | PEND | TP/ED/17/0443 | 2018 | 2018 | 2018 | 2018 | 16 | 0 | 16 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | LEGAL
2019 | ED0174A | LENZIE HOSPITAL (AUCHINLOCH ROAD) | LENZIE | 266014 | 671084 | SGNE | ST | 3.4 | PRIV | ROBERTSON HOMES Ltd | PRIV | OO |  |  |  | ROBERTSON HOMES Ltd | COMM |  | NB-BNU | DETL | TP/ED/16/0330 | 2017 | 2017 | 2017 | 2017 | 49 | 31 | 18 |  |  |  | 0 | 0 | 0 | 5 | 26 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | UNCON
2019 | ED0087 | MAIN STREET (FORMER GARAGE) | TORRANCE | 262049 | 674133 | SGNE | ST | 0.29 | PRIV | R K PROPERTIES (SCOTLAND) Ltd | SR |  | RSL |  |  | TRUST HOUSING ASSOCIATION | COMM |  | NB-BU | DETL | TP/ED/17/0821 | 2010 | 2010 | 2013 | 2013 | 19 | 0 | 19 |  |  |  | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | UNCON
2019 | ED0093 | BARRHILL LODGE/ CANALSIDE | TWECHAR | 269992 | 675926 | SGNE | ST | 0.14 | MIX | EDC & PRIVATE OWNERS | SR |  | RSL |  |  | CASTLE ROCK EDINVAR HOUSING ASSOCIATION | ALPS |  | NB-BU |  |  | 2010 | 2010 | 2014 | 2014 | 21 | 0 | 21 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 11 | 21 | 0 | 0 | OWN
2019 | ED0174B | LENZIE HOSPITAL (AUCHINLOCH ROAD) | LENZIE | 266014 | 671084 | SGNE | ST | 0.1 | PRIV | ROBERTSON HOMES Ltd | PRIV | OTH |  | SO | RSL | BIELD | COMM |  | NB-BNU | DETL | TP/ED/16/0330 | 2017 | 2017 | 2017 | 2017 | 24 | 3 | 21 |  |  |  | 0 | 0 | 0 | 0 | 3 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | UNCON
2019 | ED0099B | CADDER WORKS/ JELLYHILL | BISHOPBRIGGS | 261284 | 671859 | SGNE | ST | 2.3 | PRIV | CALA HOMES WEST SCOTLAND LTD | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | CONS |  | NB-BU | DETL | TP/ED/17/0051 | 2012 | 2012 | 2015 | 2015 | 22 | 0 | 22 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | UNCON
2019 | ED0161B | BRAE'S OF YETTS | KIRKINTILLOCH | 268034 | 673733 | SGNE | ST | 1.5 | PRIV | BARRATT WEST SCOTLAND | SR |  | RSL |  |  | HILLHEAD HOUSING ASSOCIATION | CONS |  | NB-GU | DETL | TP/ED/16/0600 | 2015 | 2015 | 2015 | 2015 | 22 | 0 | 22 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | UNCON
2019 | ED0193 | 38 KILSYTH ROAD | KIRKINTILLOCH | 266411 | 674438 | SGNE | ST | 0.33 | RSL | LINK HOUSING ASSOCIATION | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | PROP |  | NB-BU |  |  | 2019 | 2019 | 2019 | 2019 | 23 | 0 | 23 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | 0 | 0 | 23 | 0 | 0 | PHY
2019 | ED0104 | KELVIN VIEW | TORRANCE | 262321 | 673851 | SGNE | ST | 1.21 | PRIV | UNKNOWN | SR |  | RSL |  |  | CLYDE VALLEY HOUSING ASSOCIATION | ALPS |  | NB-GNU |  |  | 2012 | 2012 | 2012 | 2012 | 25 | 0 | 25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | FUND
2019 | ED0170A | CROFTHEAD (NORTH BISHOPBRIGGS) | BISHOPBRIGGS | 262050 | 672339 | SGNE | ST | 1.9 | PRIV | CALEDONIAN PROPERTIES LTD | PRIV | OO |  |  |  | MACTAGGART & MICKEL HOMES LTD | ALPS |  | NB-BNU |  |  | 2017 | 2017 | 2017 | 2017 | 25 | 0 | 25 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 15 | 0 | 0 | 0 | 25 | 0 | 0 | OTH
2019 | ED0171A | CHRYSTON ROAD SOUTH (FAULDHEAD) | KIRKINTILLOCH | 267777 | 672745 | SGNE | ST | 3.15 | PRIV | CALA HOMES WEST SCOTLAND Ltd | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND Ltd | ALPS |  | NB-GU |  |  | 2017 | 2017 | 2017 | 2017 | 26 | 0 | 26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 26 | 0 | 0 | MARK
2019 | ED0151B | CLADDENS SOUTH | LENZIE | 266493 | 671517 | SGNE | ST | 2.2 | PRIV | CALA HOMES WEST SCOTLAND Ltd | SR |  | LA |  |  | EDC | CONS |  | NB-GU | DETL | TP/ED/17/0517 | 2015 | 2015 | 2015 | 2015 | 26 | 0 | 26 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 10 | 0 | 0 | 0 | 26 | 0 | 0 | UNCON
2019 | EDBM0073C | KILMARDINNY - AFFORDABLE SITE 1 | BEARSDEN | 255543 | 673222 | GGNW | BM | 0.5 | LA | EDC | SR |  | LA |  |  | EDC | COMM |  | NB-BU | DETL | TP/ED/17/0933 | 1993 | 1993 | 1993 | 2011 | 27 | 0 | 27 |  |  |  | 0 | 0 | 0 | 0 | 0 | 8 | 19 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | UNCON
2019 | ED0192 | HUNTERSHILL | BISHOPBRIGGS | 261014 | 669612 | SGNE | ST | 1.3 | LA | EDC | SR |  | LA |  |  | EDC | PROP |  | NB-BU |  |  | 2019 | 2019 | 2019 | 2019 | 29 | 0 | 29 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 13 | 0 | 0 | 29 | 0 | 0 | PHY
2019 | ED0102A | MEADOWBURN AVENUE | LENZIE | 266569 | 671984 | SGNE | ST | 2.55 | PRIV |  | PRIV | OO |  |  |  | MILLER HOMES | ALPS |  | NB-GNU |  |  | 2012 | 2012 | 2012 | 2012 | 30 | 0 | 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 30 | 0 | 0 | PHY
2019 | ED0140A | THORN ROAD (GOLF COURSE) | BEARSDEN | 253235 | 672195 | GGNW | BM | 3 | PRIV | BEARSDEN GOLF CLUB | PRIV | OO |  |  |  | ROBERTSON HOMES LTD | ALPS |  | NB-GU |  | TP/ED/19/0067 | 2015 | 2015 | 2015 | 2015 | 30 | 0 | 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 30 | 0 | 0 | INFRA
2019 | ED0142B | CRAIGTON ROAD (CLOBER GOLF CLUB) | MILNGAVIE | 254616 | 675165 | GGNW | BM | 1 | PRIV | CLOBER GOLF CLUB | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 30 | 0 | 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 20 | 0 | 0 | 30 | 0 | 0 | INFRA
2019 | ED0078C | ROB ROY FC / ADAMSLIE - PHASE 2 | KIRKINTILLOCH | 264455 | 673715 | SGNE | ST | 1.34 | PRIV | DAWN HOMES Ltd | PRIV | OO |  |  |  | DAWN HOMES Ltd | CONS |  | NB-BU | DETL | TP/ED/17/0052 | 2008 | 2008 | 2008 | 2008 | 30 | 0 | 30 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | INFRA
2019 | ED0153B | CHRYSTON ROAD NORTH (FAULDHEAD) | KIRKINTILLOCH | 267600 | 673013 | SGNE | ST | 0.1 | PRIV | CALA HOMES WEST SCOTLAND Ltd | SR |  | RSL |  |  | UNKNOWN | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 31 | 0 | 31 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 16 | 0 | 0 | 31 | 0 | 0 | MARK
2019 | ED0038B | BROOMHILL HOSPITAL SITE | KIRKINTILLOCH | 266210 | 674539 | SGNE | ST | 10.88 | PRIV | CALA HOMES WEST SCOTLAND Ltd | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | ALPS |  | NB-BU | PEND | TP/ED/17/0857 | 2003 | 2003 | 2003 | 2014 | 33 | 0 | 33 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | UNCON
2019 | ED0156 | KERR STREET (LAIRDSLAND SCHOOL) | KIRKINTILLOCH | 265270 | 673830 | SGNE | ST | 0.3 | LA | EDC | SR |  | LA |  |  | EDC | ALPS |  | CONV-U |  |  | 2015 | 2015 | 2015 | 2015 | 38 | 0 | 38 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | PHY
2019 | ED0175A | BIRDSTON ROAD | MILTON OF CAMPSIE | 265261 | 675888 | SGNE | ST | 3.1 | PRIV | CALA HOMES WEST SCOTLAND Ltd | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND Ltd | COMM |  | NB-GU | DETL | TP/ED/17/0486 | 2017 | 2017 | 2017 | 2017 | 43 | 4 | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25 | 14 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | UNCON
2019 | ED0173A | LENNOXLEA | LENNOXTOWN | 263473 | 677085 | SGNE | ST | 3 | PRIV | TAYLOR WIMPEY WEST SCOTLAND Ltd | PRIV | OO |  |  |  | TAYLOR WIMPEY WEST SCOTLAND Ltd | ALPS |  | NB-GU |  |  | 2017 | 2017 | 2017 | 2017 | 40 | 0 | 40 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 40 | 0 | 0 | MARK
2019 | EDBM0073E | KILMARDINNY - CALA PHASE 2 | BEARSDEN | 255699 | 673187 | GGNW | BM | 4.13 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | COMM |  | NB-GU | DETL | TP/ED/15/0928 | 1993 | 1993 | 1993 | 2011 | 62 | 22 | 40 |  |  |  | 0 | 0 | 0 | 1 | 21 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | UNCON
2019 | ED0182A | HIGH STREET VAN HIRE (NO'S 62 - 72) PHASE 1 | KIRKINTILLOCH | 265413 | 674144 | SGNE | ST | 0.27 | PRIV | UNKNOWN | SR |  | RSL |  |  | CLYDE VALLEY HOUSING ASSOCIATION | COMM |  | NB-BU | DETL | TP/ED/16/0466 | 2017 | 2017 | 2017 | 2017 | 41 | 0 | 41 |  |  |  | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | UNCON
2019 | ED0188A | ST MUNGO STREET | BISHOPBRIGGS | 260902 | 669985 | SGNE | ST | 0.5 | PRIV | CARMICHAEL HOMES & INTERIORS | PRIV | OO |  |  |  | CARMICHAEL HOMES & INTERIORS | COMM |  | NB-BU | DETL | TP/ED/17/0717 | 2018 | 2018 | 2018 | 2018 | 48 | 0 | 48 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 13 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | UNCON
2019 | ED0151A | CLADDENS SOUTH | LENZIE | 266493 | 671514 | SGNE | ST | 5 | PRIV | CALA HOMES WEST SCOTLAND Ltd | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND Ltd | CONS |  | NB-GU | DETL | TP/ED/17/0517 | 2015 | 2015 | 2015 | 2015 | 48 | 0 | 48 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 25 | 13 | 0 | 0 | 0 | 48 | 0 | 0 | UNCON
2019 | ED0055A | CRAIGDHU RD, FIRE STATION FIELD | MILNGAVIE | 254497 | 674201 | GGNW | BM | 0.65 | PRIV | MCCARTHY & STONE | PRIV | OO |  |  |  | MCCARTHY & STONE | COMM |  | NB-GU | DETL | TP/ED/16/0823 | 2005 | 2017 | 2005 | 2017 | 49 | 0 | 49 |  |  |  | 0 | 0 | 0 | 0 | 0 | 25 | 24 | 0 | 0 | 0 | 0 | 0 | 49 | 0 | 0 | UNCON
2019 | ED0154 | GLASGOW ROAD | KIRKINTILLOCH | 265198 | 674246 | SGNE | ST | 1.2 | LA | EDC | SR |  | LA |  |  | EDC | ALPS |  | NB-BU |  |  | 2015 | 2015 | 2015 | 2015 | 60 | 0 | 60 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 15 | 0 | 0 | 0 | 60 | 0 | 0 | PHY
2019 | EDBM0073A | KILMARDINNY - ROBERTSON | BEARSDEN | 255584 | 673251 | GGNW | BM | 4.5 | PRIV | ROBERTSON HOMES LTD | PRIV | OO |  |  |  | ROBERTSON HOMES LTD | COMM |  | NB-GU | DETL | TP/ED/15/0944 | 1993 | 1993 | 1993 | 2011 | 70 | 1 | 69 |  |  |  | 0 | 0 | 0 | 0 | 1 | 30 | 30 | 9 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | UNCON
2019 | ED0152 | CLEDDENS PLAYING FIELD | KIRKINTILLOCH | 266747 | 674494 | SGNE | ST | 1.4 | MIX | EDC & BIELD | SR |  | LA |  |  | EDC | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 76 | 0 | 76 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 26 | 0 | 0 | 0 | 76 | 0 | 0 | UNCON
2019 | ED0161A | BRAE'S OF YETTS | KIRKINTILLOCH | 268034 | 673733 | SGNE | ST | 9.8 | PRIV | BARRATT WEST SCOTLAND | PRIV | OO |  |  |  | BARRATT WEST SCOTLAND | COMM |  | NB-GU | DETL | TP/ED/16/0600 | 2015 | 2015 | 2015 | 2015 | 92 | 11 | 81 |  |  |  | 0 | 0 | 0 | 0 | 11 | 30 | 30 | 21 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | UNCON
2019 | ED0142A | CRAIGTON ROAD (CLOBER GOLF CLUB) | MILNGAVIE | 254616 | 675165 | GGNW | BM | 4.9 | PRIV | CLOBER GOLF CLUB | PRIV | OO |  |  |  | STEWART MILNE HOMES (CENTRAL) | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 90 | 0 | 90 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 0 | 90 | 0 | 0 | INFRA
2019 | ED0153A | CHRYSTON ROAD NORTH (FAULDHEAD) | KIRKINTILLOCH | 267600 | 673013 | SGNE | ST | 14.9 | PRIV | CALA HOMES WEST SCOTLAND Ltd | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND Ltd | ALPS |  | NB-GU |  |  | 2015 | 2015 | 2015 | 2015 | 94 | 0 | 94 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 36 | 36 | 0 | 94 | 0 | 0 | MARK
2019 | ED0099A | CADDER WORKS/ JELLYHILL | BISHOPBRIGGS | 260947 | 671671 | SGNE | ST | 4.53 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | CONS |  | NB-BU | DETL | TP/ED/17/0051 | 2012 | 2012 | 2015 | 2015 | 101 | 0 | 101 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30 | 30 | 11 | 0 | 101 | 0 | 0 | UNCON
2019 | ED0038A | BROOMHILL HOSPITAL SITE | KIRKINTILLOCH | 266070 | 674555 | SGNE | ST | 10.88 | PRIV | CALA HOMES WEST SCOTLAND Ltd | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND Ltd | ALPS |  | NB-GU | PEND | TP/ED/17/0857 | 2003 | 2003 | 2003 | 2014 | 118 | 0 | 118 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 30 | 30 | 30 | 18 | 0 | 118 | 0 | 0 | UNCON
2019 | ED0041B | LENNOX CASTLE HOSPITAL PHASE 1B & 2 | LENNOXTOWN | 260606 | 678302 | SGNE | ST | 3.94 | OTH | NHS | PRIV | OO |  |  |  | PERSIMMON HOMES (WEST SCOTLAND) | ALPS |  | NB-BNU |  | TP/ED/17/0407 | 2003 | 2003 | 2003 | 2014 | 136 | 0 | 136 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 40 | 40 | 31 | 0 | 136 | 0 | 0 | PHY

## 2018-19 Completions
UPDTYEAR | SITE_REF | ADDRESS1 | ADDRESS2 | EASTING | NORTHING | HMSA | LASUB | SITE_SIZE | OWNER1 | OWNER2 | TENURE | PRIVTEN | SRTEN | INTTEN | TENNOTE | BUILDER | PLANSTAT | SPGR | DEVTYPE | CONSENT | APP | FST_IN_ELS | CON_IN_ELS | FST_IN_EFF | CON_IN_EFF | CAPACITY | TOTAL_BUILT | REMAINDER | COMPLETIONS PRE 2012 | 2012-13 | 2013-14 | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19 | 2019-20 | 2020-21 | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | TOTAL 7 YEAR PROGRAMMING | POST_7YEAR | DISPUTED | SITE_CONSTRAINTS
2019 | ED0045A | CALICO WAY / WHITEFIELD TERR | LENNOXTOWN | 262202 | 678108 | SGNE | ST | 1.1 | RSL | LINK HOUSING ASSOCIATION | SR |  | RSL |  |  | LINK HOUSING ASSOCIATION | COMP |  | NB-BU | DETL | TP/ED/15/0347 | 2001 | 2001 | 2001 | 2015 | 32 | 32 | 0 |  |  |  | 0 | 0 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNCON
2019 | EDSK0278I | WOODILEE VILLAGE P2 E SPRINGFIELD | LENZIE | 266799 | 672523 | SGNE | ST | 3.9 | PRIV | SPRINGFIELD PROPERTIES PLC | PRIV | OO |  |  |  | SPRINGFIELD PROPERTIES PLC | COMP | 1990 | NB-GNU | DETL | TP/ED/06/1294 | 1992 | 1992 | 2005 | 2012 | 133 | 133 | 0 |  |  | 8 | 19 | 18 | 38 | 35 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNCON
2019 | ED0045B | CALICO WAY / WHITEFIELD TERR | LENNOXTOWN | 262202 | 678108 | SGNE | ST | 0.21 | RSL | LINK HOUSING ASSOCIATION | PRIV | OTH |  | SE |  | LINK HOUSING ASSOCIATION | COMP |  | NB-BU | DETL | TP/ED/15/0347 | 2001 | 2001 | 2001 | 2015 | 12 | 12 | 0 |  |  |  | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNCON
2019 | ED0179 | LEDCAMEROCH ROAD (No26) | BEARSDEN | 253735 | 671925 | GGNW | BM | 0.57 | PRIV | LEDCAMEROCH HOMES LTD | PRIV | OO |  |  |  | LEDCAMEROCH HOMES LTD | COMP |  | NB-BU | DETL | TP/ED/15/0095 | 2017 | 2017 | 2017 | 2017 | 9 | 9 | 0 |  |  |  | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNCON
2019 | EDSK0278G | WOODILEE VILLAGE ADMIN BLOCK | LENZIE | 266653 | 672557 | SGNE | ST | 0.1 | PRIV | PERSIMMON HOMES (WEST SCOTLAND) | PRIV | OO |  |  |  | PERSIMMON HOMES (WEST SCOTLAND) | COMP | 1990 | CONV-NU | DETL | TP/ED/12/0644 | 1992 | 1992 | 2005 | 2012 | 7 | 7 | 0 |  |  |  | 0 | 0 | 0 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNCON
2019 | ED0189 | MAIN STREET MILNGAVIE (No52) | MILNGAVIE | 255308 | 674170 | GGNW | BM | 0.1 | PRIV | ADAM (SCOTLAND) LTD | PRIV | OO |  |  |  | ADAM (SCOTLAND) LTD | COMP |  | NB-BU | DETL | TP/ED/17/0075 | 2018 | 2018 | 2018 | 2018 | 6 | 6 | 0 |  |  |  | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | UNCON
2019 | ED0168A | BIRNAM CRESCENT | BEARSDEN | 256043 | 672264 | GGNW | BM | 2.3 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | COMM |  | NB-GU | DETL | TP/ED/17/0511 | 2017 | 2017 | 2017 | 2017 | 15 | 1 | 14 |  |  |  | 0 | 0 | 0 | 0 | 1 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | UNCON
2019 | EDBM0073A | KILMARDINNY - ROBERTSON | BEARSDEN | 255584 | 673251 | GGNW | BM | 4.5 | PRIV | ROBERTSON HOMES LTD | PRIV | OO |  |  |  | ROBERTSON HOMES LTD | COMM |  | NB-GU | DETL | TP/ED/15/0944 | 1993 | 1993 | 1993 | 2011 | 70 | 1 | 69 |  |  |  | 0 | 0 | 0 | 0 | 1 | 30 | 30 | 9 | 0 | 0 | 0 | 0 | 69 | 0 | 0 | UNCON
2019 | ED0174B | LENZIE HOSPITAL (AUCHINLOCH ROAD) | LENZIE | 266014 | 671084 | SGNE | ST | 0.1 | PRIV | ROBERTSON HOMES Ltd | PRIV | OTH |  | SO | RSL | BIELD | COMM |  | NB-BNU | DETL | TP/ED/16/0330 | 2017 | 2017 | 2017 | 2017 | 24 | 3 | 21 |  |  |  | 0 | 0 | 0 | 0 | 3 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | UNCON
2019 | ED0175A | BIRDSTON ROAD | MILTON OF CAMPSIE | 265261 | 675888 | SGNE | ST | 3.1 | PRIV | CALA HOMES WEST SCOTLAND Ltd | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND Ltd | COMM |  | NB-GU | DETL | TP/ED/17/0486 | 2017 | 2017 | 2017 | 2017 | 43 | 4 | 39 |  | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 25 | 14 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | UNCON
2019 | ED0163 | LOCHMILL FARM- ANTERMONY ROAD | MILTON OF CAMPSIE | 266716 | 676438 | SGNE | ST | 0.73 | PRIV | HCS CONSTRUCTION | PRIV | OO |  |  |  | HCS CONSTRUCTION | COMM |  | CONV-NU | DETL | TP/ED/13/0382 | 2016 | 2016 | 2016 | 2016 | 8 | 6 | 2 |  |  |  | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | UNCON
2019 | ED0161A | BRAE'S OF YETTS | KIRKINTILLOCH | 268034 | 673733 | SGNE | ST | 9.8 | PRIV | BARRATT WEST SCOTLAND | PRIV | OO |  |  |  | BARRATT WEST SCOTLAND | COMM |  | NB-GU | DETL | TP/ED/16/0600 | 2015 | 2015 | 2015 | 2015 | 92 | 11 | 81 |  |  |  | 0 | 0 | 0 | 0 | 11 | 30 | 30 | 21 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | UNCON
2019 | ED0177A | WEST CARLSTON GARDEN CENTRE (CAMPSIE ROAD) | TORRANCE | 262506 | 674576 | SGNE | ST | 1.01 | PRIV | DAWN HOMES LTD | PRIV | OO |  |  |  | DAWN HOMES LTD | COMM |  | NB-BNU | DETL | TP/ED/16/0325 | 2017 | 2017 | 2017 | 2017 | 16 | 14 | 2 |  |  |  | 0 | 0 | 0 | 0 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | UNCON
2019 | ED0178 | SWITCHBACK RD (No8) | BEARSDEN | 254730 | 670909 | GGNW | BM | 0.37 | PRIV | MCCARTHY & STONE RETIREMENT LIFESTYLES Ltd | PRIV | OO |  |  |  | MCCARTHY & STONE RETIREMENT LIFESTYLES Ltd | COMM |  | NB-BU | DETL | TP/ED/16/0293 | 2017 | 2017 | 2017 | 2017 | 23 | 18 | 5 |  |  |  | 0 | 0 | 0 | 0 | 18 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | UNCON
2019 | EDBM0073E | KILMARDINNY - CALA PHASE 2 | BEARSDEN | 255699 | 673187 | GGNW | BM | 4.13 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | COMM |  | NB-GU | DETL | TP/ED/15/0928 | 1993 | 1993 | 1993 | 2011 | 62 | 22 | 40 |  |  |  | 0 | 0 | 0 | 1 | 21 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | UNCON
2019 | ED0144A | INVERORAN DRIVE (KESSINGTON) | BEARSDEN | 256092 | 671451 | GGNW | BM | 2.5 | PRIV | MANSELL HOMES | PRIV | OO |  |  |  | MANSELL HOMES | COMM |  | NB-GU | DETL | TP/ED/14/0602 | 2015 | 2015 | 2015 | 2015 | 59 | 56 | 3 |  |  |  | 0 | 0 | 7 | 27 | 22 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | UNCON
2019 | ED0174A | LENZIE HOSPITAL (AUCHINLOCH ROAD) | LENZIE | 266014 | 671084 | SGNE | ST | 3.4 | PRIV | ROBERTSON HOMES Ltd | PRIV | OO |  |  |  | ROBERTSON HOMES Ltd | COMM |  | NB-BNU | DETL | TP/ED/16/0330 | 2017 | 2017 | 2017 | 2017 | 49 | 31 | 18 |  |  |  | 0 | 0 | 0 | 5 | 26 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | UNCON
2019 | EDBM0073B | KILMARDINNY - CALA PHASE 1 | BEARSDEN | 255584 | 673251 | GGNW | BM | 3.72 | PRIV | CALA HOMES WEST SCOTLAND LTD | PRIV | OO |  |  |  | CALA HOMES WEST SCOTLAND LTD | COMM |  | NB-BU | DETL | TP/ED/13/0686 | 1993 | 1993 | 1993 | 2011 | 135 | 123 | 12 |  |  |  | 0 | 0 | 2 | 61 | 60 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | UNCON